## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | CONFIDE Instant Messaging Service |  | LAST REVIEW: | 2017-05-03 |  | Project Name: | CONFIDE Instant Messaging Service
National Center: |  |  | Australia |  |  |  |  | National Center: | Australia
Project Manager Name: |  |  | Team Orange |  |  |  |  | Project Manager Name: | Team Orange
Project Description: |  |  | Build Instant Messaging Service Client |  |  |  |  | Project Description: | Build Instant Messaging Service Client
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
1 | Closed | High | Medium | Closed | Current Project has not selected a suitable XMPP Client API. There are 3 initially suitable Java implementations, which are Babbler, Emite GWT and Smack. | If suitable Client APIs do not meet critical Non-Functional Requirements, it would cause major resourcing constraints on project to investigate and implement and test another API. | Feasibility | Not identified and tested Client API. | If API is not verified suitable by end of Elaboration implement contingency plan. | Mitigation | Identify suitable API ASAP in project planning. | Lower scope of implementation and/or find another suitable API with less scope to meet project outcomes.
2 | Open | Medium | Medium | Yellow | Underestimating Key deliverable resourcing. | If Key deliverable requires more resourcing than estimate, it will impact other deliverables in project. | Project Resources | Not correctly identifying resourcing requirement of deliverable. | Iteration mid-weekly review | Acceptance | Test critical components for project in elaboration phase. emphasis of Key architectural components, where scope is harder to change. | Deliverable is descoped or removed.
3 | Open | Medium | Medium | Yellow | Misunderstanding of deliverable's functional or non-functional requirements. | System component(s) not providing intended function, not meeting project outcomes and affect other System Components. | Project Management | Deliverable is not fit for purpose | Code review, integration testing, Iteration Review | Mitigation | Team member educated on the problems(s) corrects the quality of deliverable. | Deliverable is descoped, removed and/or given to other team member to complete.
4 | Open | Medium | Medium | Yellow | Deliverable does not meet the project's quality standards | System component(s) may introduce errors and/or degradation of functionality. Design changes may be harder to implement due to poor dependency management, code is difficult to refactor | Reliability of Systems | Deliverable does not meet quality requirements. | Code review, integration testing, Iteration Review | Mitigation | Quality standards revisited by team. Team member commits to following project quality standards | Team member assigned to less complex tasks. Team member's work is more rigorously inspected in the short term to confirm that quality standards are being adhered to
5 | Open | Medium | Medium | Yellow | Deliverable is too difficult to solve in time frame for team member skill set. | System components not providing intended function, not meeting project outcomes and affect other System Components. | Project Resources | Deliverable does not meet quality requirements. | Team member notifies project of difficulties with problem. | Mitigation | Suitable Team member provide assistance with deliverable. | Deliverable is descoped/removed/reassigned.
6 | Open | High | Medium | Red | Team member being unavailable for project. | Project deliverables being delayed. | Schedule | Team member is unavailable to perform deliverable for iteration. | Team member notifies project of unavailability | Mitigation | Delaying deliverable. | Deliverable is descoped/removed/reassigned.
7 | Open | High | High | Red | High level of technical complexity | Project deliverables could not being met. | Technology | Learning curve for architectural components is too high. | Team members identifying complexity of tasks. | Mitigation | Choose suitable architectural components which encapsulate complexities of base components. | Deliverable is descoped/removed/reassigned.
8 | Open | Medium | Medium | Yellow | Ineffective communications | Unnecessary delays, project milestones not met, contingency plans cannot be enacted | Project Management | Lack of coordination, duplicated effort, wasted time and resources | Communication issues noted during each iteration review. Project team follows performance management procedures from Team Charter | Mitigation | Team member(s) reminded of team charter communication agreement. Team members commit to using available communication mechanisms in an effective and timely manner. | Performance management according to team charter. Under extreme circumstances removal of repeat offender from project.
9 | Open | High | Medium | Red | Late deliverables | Extended delays in delivery of project. Critical path items delay all team members | Project Management | Team members unable to complete tasks, chasing deliverables | Iteration mid-weekly review | Mitigation | Team member(s) reminded of team charter agreement. Team members not delivering on time provide commitment and steps to address the problem | Performance management according to team charter. Under extreme circumstances removal of repeat offender from project.
10 | Open | Low | Low | Green | Changing scope / objectives | Not meeting high level business goals and function requirements. | Overall Project Failure | Client identifies requirements that are not listed in the project plan | Not meeting client's objective in iteration review. | Avoidance | Team ensures sign-off from client on the scope/deliverables. Additional features proposed by the client are identified as outside the scope. | Negotiate with the client for extension of project schedule and/or resources in order to meet the changed scope
11 | Open | Medium | Low | Green | Software components do not interface with each other correctly | Project deliverables could not being met or delayed. | Overall Project Failure | Project components cannot interface. | Team members identify issues with interfacing. | Avoidance | Architectural design and design/code conventions well documented. Ensure effective communication before building components. Communicate any exceptions or deviations from established conventions. Build and test regularly to identify problems | Rectify components.
12 | Open | High | Low | Yellow | NFRs not being met | Not meeting high level business goals and function requirements. | Overall Project Failure | Testing reveals that NFR requirement not being met. | Consistently not meeting objective in iteration reviews. | Avoidance | Ensure Client API and Server Implementations meet NFR requirements according to available documentation and user reviews. Implement the most critical features first and identify mitigation strategies/workarounds for problems identified. | Deliverable is descoped/removed/reassigned.
13 | Closed | Medium | Low | Closed | Client API is to difficult/time consuming to learn | Project deliverables could not being met or delayed. | Project Resources | difficulty keeping up with schedule, as to much time is spent on client api | Consistently not meeting objective in iteration reviews. | Mitigation | Identify early (E-1) and change to a more suitable client api | Change to another of the 3 identified possible client api's
14 | Open | Medium | Medium | Yellow | Client API does not meet all the project needs | Project deliverables could not being met or delayed. | Technology | Some use cases cannot be met because the client api is not sufficient | Team members identify issues with client api's ability to implement a specific use case | Avoidance | Identify early (E-1) and change to a more suitable client api | Change to another of the 3 identified possible client api's
15 | Closed | Low | Medium | Closed | Server is to difficult/time consuming to learn | Project deliverables could not being met or delayed. | Project Resources | difficulty keeping up with schedule, as to much time is spent on server | Consistently not meeting objective in iteration reviews. | Mitigation | Identify early (E-1) and change to a more suitable server | Change to another of the identified possible servers
16 | Open | Low | Low | Green | Server does not meet all the project needs | Project deliverables could not being met or delayed. | Technology | Some use cases cannot be met because the server is not sufficient | Team members identify issues with servers ability to implement a specific use case | Avoidance | Identify early (E-1) and change to a more suitable server | Change to another of the identified possible servers
17 | Closed | Low | Low | Green | Trouble keeping development environments in sync accross multiple computers and OS's | More difficultycollaborating, wastes time and slows development. | Project Management | Development environments begin to differ. Some things work on one persons environment but not anothers | Team members notice that development environments are drifting apart. | Avoidance | Use cross platform technologies such as eclipse and java. | Hold a team meeting, in which efforts are made to get development environments back in sync, and keep them there
18 | Closed | Medium | Medium | Closed | Problem with contact implementation/adding contact. See this document for further details https://github.com/csuproject/instantmessenger/blob/master/docs/Elaboration/ContactProblemFindings.docx | this is a critical core use case. Failure to resolve could require sigificant rework and subsitution of the XMPP library | Technology |  | this bug was not apparent until E3. | Mitigation | extensive testing identified that the server and XMPP library appeared to be okay - project-specific code was changed whihc solved the problem.
19
20
21
22
23
24
25
26
27
28
29
30
[5 empty] | EXAMPLE: Current project skill set may not be adequate to complete all project work. The current development team has been working in a Windows 2k environment, and the current requirements are for a LINUX environment. The project schedule would require 1500 development hours of a skilled LINUX operator, and approximately 1900 to 2200 if we retrain our current resources. | EXAMPLE: If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. |  | EXAMPLE: Schedule approaches the required start date with no identification of required skill sets. | EXAMPLE: Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. |  | EXAMPLE: Find internal resource that meets required skill set or train existing resources on LINUX. | EXAMPLE: Find resource that meets required skill set through external hiring sources.

## Review Comments
Reviewer | Date | Change | Cell / Row / Column / ID | Comments
Murray | 2017-03-31 | Formatting | All | Re-added borders on to cells, added borders to conditional formatted cells (first two columns)
Murray | 2017-03-31 | Formatting | Rows 1-6 | Freeze top 6 rows to prevent scrolling
Murray | 2017-03-31 | Revision | ID 3/4 | Split misunderstanding of deliverable and poor quality of deliverable into two separate risks. I think the first can be due to ignorance or a simple misunderstanding. The second is due to lack of skill and/or sloppiness
Murray | 2017-03-31 | General | All | spell check and general proofreading
Murray | 2017-03-31 | Revision | Contingency Column | I think we can add "reassign" to some of the contingencies. e.g. "deliverable is too difficult for team member skill set" rather than limiting to descope/remove, reassignment (or swapping tasks) may result in still achieving the overall goal. Added more information to some relating to the Triggers column.
Murray | 2017-03-31 | Revision | ID 8 | Ineffective communications separated from work item not delivered on time. The reason being the work item may have been delivered on time but project can still be impacted due to other team members not aware of it, hence unnecessary delay. Communication risk impact changed to medium (maybe should be high?)
Murray | 2017-03-31 | Revision | ID 9
Murray | 2017-03-31 | Revision | Triggers | From Instructions, this is how we decide whether to enact the contingency plan. I have added more detail to most of these
Murray | 2017-03-31 | Revision | ID 11 | Re-worded some of the columns
Murray | 2017-03-31 | Revision | ID10 | Not sure I really understood this one in the original way it was presented. Real projects can experience scope creep and this is normally due to a lack of precision in identifying requirements either on the sponsor side or the project team side. One way this can be mitigated is for the project team to produce a "return brief". This is a statement of work and normally includes a schedule. It also is a last chance for the sponsor to say "oh I've just realised you didn't understand what I really wanted". In our case because the need/ sponsor is fictious, there is no real chance of scope creep, we can only fail to deliver what we planned, however I think its good to add this for completeness
Murray | 2017-06-09 | Revision | various | Closed some risks that have been solved
Murray | 2017-06-09 | Revision | E18 | Added some details for the add contact bug
Murray | 2017-06-09 | Revision | Cell G2 | Added last review date.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources